## README
About this tool
This is a simple & flexible tool for housing a Scrum product backlog.
The main feature is that includes a "generate index cards" button.
This tool was created by Stefan Nijenhuis, with minor tweaks by me.
The design of this tool and the index cards is based on my book "Scrum and XP from the Trenches", and the first version of the index card generator on my blog (http://blog.crisp.se/henrikkniberg)
To learn more about the intended usage of this tool, see the chapter on product backlogs.
http://www.crisp.se/henrik.kniberg/ScrumAndXpFromTheTrenches.html
Feel free to use and modify this tool as you wish.
Worksheets
BACKLOG = the actual product backlog. Add columns as you like.
CARDS = index cards appear here when you press "generate index cards" on the BACKLOG worksheet.
TEMPLATE = play with this to change the appearance of the generated index cards.
If you make any significant improvements or bugfixes (while still keeping it simple) I'd appreciate if you email me at henrik.kniberg @crisp.se so that I can spread it to the community.
Thanks Stefan for implementing this!
/Henrik Kniberg 2007-12-13

## BACKLOG
ID | Imp | Name | Notes | How to test | Estimate
1 | 30 | Deposit | Need a UML sequence diagram. No need to worry about encryption for now. | Log in, open deposit page, deposit €10, go to my balance page and check that it has increased by €10. | 5
2 | 3 | See your own transaction history | Use paging to avoid large DB queries. Design similar to view users page. | Log in, click on "transactions”. Do a deposit. Go back to transactions, check that the new deposit shows up. | 3
3 | 5 | Embedded minesweeper | Through the menu, it should be possible to start an embedded minesweeper game. | Choose minesweeper in the menu, play a game. | 8
Note on A1: Henrik: Unique ID
Note on B1: Henrik: Importance. High = more importance. Used only for sorting in priority order. Only product owner is allowed to set this.
Note on F1: Henrik: Relative size of this story. Only the team is allowed to set this.
Generate index cards

## CARDS
Backlog Item #1
Importance
| Deposit | 30
| Notes | Estimate
| Need a UML sequence diagram. No need to worry about encryption for now. | 5
How to demo
Log in, open deposit page, deposit €10, go to my balance page and check that it has increased by €10.
Backlog Item #3
Importance
| Embedded minesweeper | 5
| Notes | Estimate
| Through the menu, it should be possible to start an embedded minesweeper game. | 8
How to demo
Choose minesweeper in the menu, play a game.
Backlog Item #2
Importance
| See your own transaction history | 3
| Notes | Estimate
| Use paging to avoid large DB queries. Design similar to view users page. | 3
How to demo
Log in, click on "transactions”. Do a deposit. Go back to transactions, check that the new deposit shows up.

## TEMPLATE
Backlog item #
Importance
| Story name description | 0
| Notes | Estimate
| Notes for this story | 0
How to demo
This explains how to demo